## Overview
Strategic Projects & KPI Dashboard
Sample built by Judah Rivera to show how I would run the CEO's projects, meetings, KPIs, and grant deliverables in one place. Sample data is illustrative; the structure is what I'd actually run.
Tab | What it does
Strategic Projects | Every initiative with owner, status, % complete, dependencies, risk flag, and next step. Mirrors a ClickUp board.
Meeting Action Log | Decisions and next steps from strategic meetings, each with an owner and a due date.
KPI Dashboard | Key metrics vs targets with a clear status, plus organizational-impact numbers.
Grant & Partner Deliverables | Funder, deliverable, due date, and reporting status for partner-funded work.
CEO Week Ahead | A simple weekly priorities and calendar snapshot for the CEO.

## Strategic Projects
Initiative | Owner | Status | % Complete | Start | Due | Depends On | Risk Flag | Next Step
2026 Impact Report | Comms | On track | 70% | 2026-06-01 | 2026-07-15 | Q2 data | Low | Draft sections 3-4
Partner grant renewal (Gainbridge) | CEO + EA | At risk | 40% | 2026-05-20 | 2026-07-05 | Budget sign-off | Medium | Chase finance for numbers
ClickUp rollout to all teams | Ops | On track | 85% | 2026-04-10 | 2026-06-30 | Training videos | Low | Final team onboarding Fri
Fall events calendar | Events | Delayed | 25% | 2026-06-05 | 2026-07-10 | Venue quotes | High | Escalate venue delay to CEO
Donor newsletter revamp | Comms | Not started | 0% | 2026-07-01 | 2026-08-01 | Brand guide | Low | Kickoff after Impact Report

## Meeting Action Log
Date | Meeting | Decision / Note | Action Item | Owner | Due | Status
2026-06-24 | Weekly Leadership | Prioritize grant renewal over events | Pull Q2 budget for grant | EA | 2026-06-27 | Done
2026-06-24 | Weekly Leadership | Impact Report ships mid-July | Draft sections 3-4 | Comms | 2026-06-30 | On track
2026-06-25 | Partner sync (Gainbridge) | They need deliverable summary | Send 1-page summary | EA | 2026-06-26 | On track
2026-06-26 | CEO 1:1 | Block Fridays for deep work | Update CEO calendar rule | EA | 2026-06-26 | Done

## KPI Dashboard
KPI | Owner | Target | Actual | Status | Notes
On-time project delivery | EA | 90% | 82% | At risk | Events slipping, recovering
CEO inbox response time | EA | < 24h | 18h | On track | Triaged twice daily
Grant deliverables on time | EA | 100% | 100% | On track | All current reports filed
Meeting actions closed in 1 wk | EA | 85% | 88% | On track | Action log enforced

## Grant & Partner Deliverables
Funder / Partner | Deliverable | Period | Due | Reporting Status | Owner
Gainbridge | Q2 impact + spend summary | Q2 2026 | 2026-07-05 | On track | EA
Women's Sports Foundation | Program participation data | H1 2026 | 2026-07-20 | Not started | EA
Corporate partner A | Co-branded announcement | Jun 2026 | 2026-06-30 | On track | Comms

## CEO Week Ahead
CEO Week Ahead — sample
Top 3 priorities | 1) Approve grant renewal numbers 2) Sign off Impact Report outline 3) Decide fall events venue
Protected time | Fridays blocked for deep work
Key meetings | Mon Leadership 10:00 ET, Wed Partner sync 13:00 ET, Thu Board prep 15:00 ET
Waiting on CEO | Events venue decision, newsletter tone approval
Travel | None this week; July board offsite itinerary in progress